# Research Project Timeline

| Stage | Activity | Estimated duration | Start date | End date | Deliverables | Comments/Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Research Design and Planning | - Finalize research - problem/questions - Develop research design - Prepare research proposal | 4 Weeks | 29 Sept 2025 | 26 Oct 2025 | - Finalized research questions and objectives - Research proposal slides - Approve research plan/timeline | Spend -1 week each on: FinBERT/FinGPT, sentiment in finance, hybrid prediction models, Malaysian studies. End with a clear conceptual framework. |
| Literature Review | - Search, capture and synthesize relevant literature - Prepare draft literature review | 3 Weeks | 27 Oct 2025 | 15 Nov 2025 | - Annotated bibliography of 10-15 key papers - Draft literature review chapter/section - Summary table of key studies (FinBERT, FinGPT, Malaysian stock prediction |  |
| Data Collection and Preparation | - Scrape financial/political news (The Star, NST, Malaysiakini, etc.) - Collect KLSE stock data - Annotate sample news heading (1-2k items) - Clean and preprocess datasets | 3 Weeks | 17 Nov 2025 | 7 Dec 2025 | - Cleaned and merged datasets: - - news_sentiment.csv (labeled Malaysian financial/political news) - stock_data.csv (KLSE stock data with indicators) - Documentation of data sources and preprocessing steps - Small labeled subset for validation (1-2k samples) | Annotation is time-consuming, plan for 1-2 hrs/day labelling. Ensure scripts for scraping and preprocessing are reusable. |
| Experiment 1 – Sentiment Model Benchmarking | - Run FinBERT & FinGPT (zero-shot and fine-tuned) - Evaluate with metrics (F1, precision, recall) - Document errors & qualitative differences | 3 Weeks | 8 Dec 2025 | 21 Dec 2025 | - Evaluation report comparing FinBERT vs FinGPT (F1, precision, recall) - Confusion matrices and bar charts of performance - Summary table of qualitative examples - Jupyter notebook/code for reproducibility | Spend ~ 1 week per model setup and 1 week analyzing & reporting results. |
| Experiment 2 – Sentiment vs Stock Movement | - Merge daily sentiment with stock returns - Preform correlation, regression, and Grange causality - Visualize and interpret results | 2 Weeks | 22 Dec 2025 | 4 Jan 2026 | - Correlation, regression, and Granger causality results - Visuals: lag correlation heatmap, sentiment vs price plots - Analytical report describing relationship strength and interpretation | Focus on clean data alignment (date matching). Automate feature aggregation (daily averages). |
| Experiment 3 – Stock Price Prediction Models | - Build LSTM/GRU baseline models - Add sentiment-enhanced features - Implement Transformer with FinGPT embeddings - Compare results (RMSE, MAE, accuracy) | 2 Weeks | 5 Jan 2026 | 18 Jan 2026 | - Trained LSTM, GRU and Transformer models - Model performance comparison table (RMSE, MAE, directional accuracy) - Visualization: predicted vs actual price trends - Technical appendix/code documentation | Most technical phase/ Plan 2 weeks for model training & tuning, 2 weeks for evaluation and visualization. |
| Synthesis, Analysis and Writing | - Integrate all results - Discuss contributions, limitations, and future work - Final draft of report - Review draft with supervisor - Final editing | 2 Weeks | 19 Jan 2026 | 31 Jan 2026 | - Integrated discussion and interpretation of findings - Final draft of research report - Abstract, introduction, and conclusion chapters polished - Supervisor feedback log and final edited version | Aim for a structured write-up. Iterate drafts with supervisor feedback |